## Slide 1
E-commerce Order Fulfillment Automation Backend
Software Project Lab-I (SWE 4304)
Backend-focused, console-based system
1

## Slide 2
Our Team
Saika Sarara
230042159
Adiba Ahsan Raiyan
230042161
Maliha Tasnim Khan
230042127
2
TEAM 13

## Slide 3
Project Overview
A Java-based console application designed to automate the internal backend workflow of an e-commerce system.
Focuses on post-placement order processing.
No customer-facing interface.
Simulates real-world backend operations: validation, inventory, billing, payment, and shipping.
3

## Slide 4
Key Features
1. Secure Admin Login
Admin-only access to the system. Passwords are stored using hashed values, not plain text. Prevents unauthorized access to backend operations.
2. Order Intake
Orders are loaded from structured JSON files. Required fields: orderId, items[], address, paymentMode. Orders are queued for processing.
3. Order Validation
Checks for valid order structure. Ensures non-empty items and positive quantities. Invalid orders are cancelled and logged with reasons.
4. Inventory Verification & Reservation
Verifies stock availability for each item. Uses a whole-order rejection policy if any item is unavailable. On failure: stock is released and order is cancelled. On success: stock is reserved.
5. Billing & Payment Processing
Calculates total cost from item prices and quantities. Generates invoice with unique ID (INV-YYYYMM-####). Simulated payment handling: COD (auto-approved), MockCard (approve/decline simulation). Payment failure triggers stock rollback and cancellation.
6. Shipping Simulation
Shipment created with unique tracking ID (TRK-########). Delivery status progresses step-by-step: PACKED → SHIPPED → OUT_FOR_DELIVERY → DELIVERED. Admin controls status updates.
4

## Slide 5
Key Features
7. Admin Dashboard
Menu-driven CLI dashboard. View all orders with status and summary. Search and filter orders by ID or status. Access order details, invoices, tracking, and logs.
8. Manual Status Control
Admin can manually update shipment status. System prevents invalid state transitions. Every update is logged for audit purposes.
9. Workflow Logging & Audit Trail
Each workflow step is logged with: timestamp, orderId, step name, outcome and message. Logs stored per order and in a master log file.
10. Reporting System
Automatically generates summary reports showing: total orders processed, successful vs cancelled orders, cancellation reasons, total revenue from completed orders. Reports stored as files for review.
11. Data Persistence
Uses file-based storage: products.json, orders.json, customers.json, invoices.json. Data is serialized when saved and deserialized when loaded. Ensures data remains available across program runs.
12. Test Scenarios
Includes seeded test data. Covers: successful order flow, invalid order, stock shortage, payment failure.
5

## Slide 6
Work Completed So Far:
Order Validation
Inventory & Stock Reservation
Invoice Generation
Payment Simulation
(COD & MockCard)
Shipment Creation
Basic Workflow Logging
6

## Slide 7
Timeline Overview (Baseline)
Planning & Design
Requirement analysis, design, proposal
Weeks 1-5
Core Backend Implementation
Validation, inventory, invoice, payment, shipment
Weeks 6-9
Supporting Features
Admin features, logging, reporting
Weeks 10-13
Testing & Refinement
Testing, debugging, final prep
Weeks 14-16
7

## Slide 8
Completed Work
Feature / Module
Planned Week(s)
Status
Notes
Secure admin login
Week 6
Completed
Hashed password authentication
Core order workflow pipeline
Weeks 6-9
Completed
Validation → inventory → invoice → payment → shipment → cancel
Order validation
Week 6
Completed
Cancels order on validation failure
Inventory verification & reservation
Week 7
Completed (Basic)
Stock check and reservation works
Invoice generation
Week 8
Completed
Total calculated correctly
Payment processing
Week 8
Completed
COD & MockCard supported
Shipment creation
Week 9
Completed
Tracking ID generated
Basic admin dashboard (CLI)
Week 10
Completed (Basic)
Menu-driven CLI
Central workflow logging
Week 10
Completed (Basic)
Single audit log (logs.txt)
File-based data persistence
Weeks 11-13
Completed (Basic)
Load/save using text files
These features represent the stable core backend pipeline implemented so far.
8

## Slide 9
Partially Completed Work
Feature / Module
Planned Week(s)
Status
Limitation
Order intake
Week 6
Partially completed
Works, but not JSON-based
Inventory rollback
Week 7
Partially completed
Clear for payment failure only
Invoice ID format
Week 8
Partially completed
Serial-based, not date-based
Shipping module
Week 9
Partially completed
Only PACKED state
Admin dashboard features
Week 10
Partially completed
No search/filter/detail views
Logging system
Week 10
Partially completed
No per-order logs
Data persistence
Weeks 11-13
Partially completed
TXT files, no customer data
Test scenarios
Weeks 14-16
Partially completed
Input-based, not formally validated
9

## Slide 10
Not Implemented Yet
Feature / Module
Planned Week(s)
Status
Admin signup / admin creation
Week 10
Not implemented
Shipment status progression
Week 9
Not implemented
Manual shipment status control
Week 10
Not implemented
Status transition rules & validation
Week 10
Not implemented
Reporting system (revenue, summaries)
Weeks 11-13
Not implemented
JSON-based storage
Weeks 11-13
Not implemented
Core features are completed, while supporting and reporting features are scheduled for later phases.
10

## Slide 11
Conclusion
We have successfully implemented the core backend functionalities, laying a strong foundation for the E-commerce Order Fulfillment Automation Backend.
Completed all initial planning and core implementation phases.
Next, we will focus on supporting features, testing, and refinement.
11